## Annual Procurement Plan
Procuring Entity Name | MINISTRY OF HOUSING URBAN DEVELOPMENT
Procurement Plan for year | 2025
Date Created | 2025-01-27
Comments | ANNUAL PROCUREMENT PLAN 2025
Estimated dates
Class | UNSPSC | Description | Ref No | Unit | Envisaged Quantity | Estimated Budget | Source of Funds | Prequalification (Y/N) | Procurement Method | Advert Publication Date | Award Date | Project Start Date | Project Completion Date
Works | 132776 | Construction of Housing and Urban Development Office Complex | 1 | 1 | 1 | 100000000 | Budgetary Provision | Yes | Selective Tendering | 2025-02-17 | 2025-04-07 | 2025-04-14 | 36 Weeks
Works | 132776 | Construction of (ODODO VILLA) 630 Housing Units in all 3 Senatorial District | 2 | 3 | 210 | 1500000000 | Budgetary Provision | Yes | Selective Tendering | 2025-02-17 | 2025-04-07 | 2025-04-14 | 36 Weeks
Works | 132776 | Construction of Mount Patti Recreation Center | 3 | 1 | 1 | 800000000 | Budgetary Provision | Yes | Selective Tendering | 2024-02-03 | 2025-04-18 | 2025-04-01 | 16 Weeks
Works | 132776 | Fencing of Aquired/Marked Area For Housing Estate Projects Across The 3 Senetorial District | 4 | 3 | 3 | 500000000 | Budgetary Provision | Yes | Selective Tendering | 2024-03-24 | 2025-05-16 | 2025-05-26 | 16 Weeks
Works | 132776 | Construction of 500 Nos Residential Housing Scheme in Lokoja | 5 | 1 | 500 | 1026900091 | Budgetary Provision | Yes | Selective Tendering | 2024-03-25 | 2025-05-17 | 2025-05-27 | 26 Weeks
Works | 132776 | Perimeter Fencing in some Selected Government Quarters/Building Across The State | 6 | 21 | 21 | 2471964540 | Budgetary Provision | Yes | Selective Tendering | 2024-03-26 | 2025-05-18 | 2025-05-28 | 16 Weeks
Works | 132776 | Constructions of Barracks in Selected Town Across 3 Senetorial Districts | 7 | 3 | 3 | 1102661535 | Budgetary Provision | Yes | Selective Tendering | 2024-03-27 | 2025-05-19 | 2025-05-29 | 16 Weeks
Works | 132776 | Post Flood Housing Estate including Its Social Ammenities (Roads, Electricity and Infractructures) | 8 | 1 | 1 | 26900091 | Budgetary Provision | Yes | Selective Tendering | 2025-04-30 | 2025-06-20 | 2025-06-26 | 12 Weeks
Works | 132776 | Construction of Open air Theatre for Art and Culture | 9 | 1 | 1 | 17601271 | Budgetary Provision | Yes | Selective Tendering | 2025-04-30 | 2025-06-20 | 2025-06-26 | 12 Weeks
Works | 132776 | Landscaping/Renovation of Civil Service Commission Compound and office Furniture | 10 | 1 | 1 | 16269175 | Budgetary Provision | Yes | Selective Tendering | 2025-07-29 | 2025-09-22 | 2025-09-30 | 12 Weeks
Works | 132776 | Renovation of Government Lodges Across the State | 11 | 21 | 21 | 134500454 | Budgetary Provision | Yes | Selective Tendering | 2025-07-29 | 2025-09-22 | 2025-09-30 | 4 weeks
Works | 132776 | Landscaping of Art and Culture Premises | 12 | 1 | 1 | 12374042 | Budgetary Provision | Yes | Selective Tendering | 2025-09-23 | 2025-11-07 | 2025-11-18 | 2 Weeks
Works | 132776 | Maintenance of Government Quarters/Offices Across the State | 13 | 21 | 21 | 1212589428 | Budgetary Provision | Yes | Selective Tendering | 2025-09-23 | 2025-11-07 | 2025-11-20 | 12 Weeks
Works | 132776 | Construction of (A)45X25m Hand Ball Court (B)25X18m Basket Ball Court (C)23X12m Volley Ball Court | 14 | 1 | 1 | 21520073 | Budgetary Provision | Yes | Selective Tendering | 2025-09-23 | 2025-11-07 | 2025-11-20 | 2 Weeks
Works | 132776 | Establishment of Material/Building/Testing Lab | 15 | 1 | 1 | 100000000 | Budgetary Provision | Yes | Selective Tendering | 2025-09-23 | 2025-11-07 | 2025-11-20 | 8 Weeks