## Sheet1
CONFLUENCE UNIVERSITY OF SCIENCE AND TECHNOLOGY OSARA, KOGI STATE
CUSTECH PROCUREMENT PLANNING 2025 (WORKS)
S/N | PROJECT DESCRIPTION | PREPARATION OF DESIGN &DRAWING | PRO. METHOD | PREPARATION OF TENDER DOCUMENT | BPP NO OBJECTION | ADVERTISEMENT | TENDER CLOSING &OPENING | EVALUATION DAY | APPROVAL OF EVALUATION REPORT | AWARD NOTIFICATION DATE | CONTRACT SIGNING DATE | CONTRACT COMMENCEMENT | CONTRACT COMPLETION DATE | CONTRACT AMOUNT
1 | CONSTRUCTION/ EQUIPPING OF ADMIN BLOCK |  | ON GOING | 2025-03-02 | 29/4/2025 |  |  | 2025-07-04 | 13/5/2025 | 14/5/2025 | 15/5/2025 | 16/5/2025 | 2025-08-08 | 1800000000
2 | CONSTRUCTION OF LECTURE HALLS & THEARTRES | 2025-03-02 | OPEN COMPETITIVE | 2025-03-03 | 21/5/2025 | 17/3/2025 | 28/4/2025 | 2025-05-05 | 22/5/2025 | 23/5/2025 | 2025-02-06 | 2025-03-06 | 24/2/2026 | 1,200,000.000.00
3 | CONSTRUCTION/ EQUIPPING OF STAFF QUARTERS (CUSTECH) | 2025-03-02 | OPEN COMPETITIVE | 2025-03-03 | 21/5/2025 | 17/3/2025 | 28/4/2025 | 2025-05-05 | 22/5/2025 | 23/5/2025 | 2025-02-06 | 2025-03-06 | 2026-02-10 | 500000000
4 | CONSTRUCTION/ EQUIPPING OF UNIVERSITY LIBRARY (CUSTECH) |  | ON GOING | 2025-03-02 | 29/4/2025 |  |  | 2025-07-04 | 13/5/2025 | 14/5/2025 | 15/5/2025 | 16/5/2025 | 2025-11-07 | 350000000
5 | CONSTRUCTION/ EQUIPPING OF UNIVERSITY CLINIC (CUSTECH) | 2025-03-02 | OPEN COMPETITIVE | 2025-03-03 | 21/5/2025 | 17/3/2025 | 28/4/2025 | 2025-05-05 | 22/5/2025 | 23/5/2025 | 2025-02-06 | 2025-03-06 | 2026-02-10 | 500000000
6 | PROVISION OF WATER FACILITIES (CUSTECH) | 2025-03-02 | OPEN COMPETITIVE | 2025-03-03 | 21/5/2025 | 17/3/2025 | 28/4/2025 | 2025-05-05 | 22/5/2025 | 23/5/2025 | 2025-02-06 | 2025-03-06 | 2025-01-07 | 25000000
7 | CONSTRUCTION/ MAINTENANCE OF STUDENT HOSTELS (CUSTECH) | 2025-03-02 | OPEN COMPETITIVE | 2025-03-03 | 21/5/2025 | 17/3/2025 | 28/4/2025 | 2025-05-05 | 22/5/2025 | 23/5/2025 | 2025-02-06 | 2025-03-06 | 24/2/2026 | 1000000000
8 | CONSTRUCTION/ EQUIPPING OF COLLEGE OF MEDICINE, FACULTY OF ENGINEERING, SENATE BUILDING & FACULTY OF COMPUTING & INFORMATION TECHNOLOGY (CUSTECH) |  | ON GOING | 2025-03-02 | 29/4/2025 |  |  | 2025-07-04 | 13/5/2025 | 14/5/2025 | 15/5/2025 | 16/5/2025 | 2025-11-07 | 1500000000
9 | CONSTRUCTION/ PROVISION OF SPORTING FACILITIES (CUSTECH) | 2025-01-02 | ON GOING | 2025-03-02 | 29/4/2025 |  |  | 2025-07-04 | 13/5/2025 | 14/5/2025 | 15/5/2025 | 16/5/2025 | 2025-11-07 | 15000000
10 | CONSTRUCTION/ PROVISION OF RECREATION FACILITIES (CUSTECH) | 2025-01-02 | RESTRICTIVE TENDERING | 2025-01-02 | 5/3/2025 10/3/2025 | 17/2/2025 | 24/2/2025 | 2025-07-03 | 17/3/2025 | 18/3/2025 | 19/3/2025 | 20/3/2025 | 2025-03-04 | 10000000
11 | REPLACEMENT/ MAINTENANCE OF ELECTRICITY EQUIPMENT |  | OPEN COMPETITIVE | 2025-03-02 | 29/4/2025 | 17/2/2025 | 31/3/2025 | 2025-07-04 | 13/5/2025 | 14/5/2025 | 15/5/2025 | 16/5/2025 | 13/6/2025 | 100000000
12 | CONSTRUCTION OF CHAIRS & TABLE TO EQUIP STUDENT LECTURE HALLS |  | OPEN COMPETITIVE | 2025-03-02 | 29/4/2025 | 17/2/2025 | 31/3/2025 | 2025-07-04 | 13/5/2025 | 14/5/2025 | 15/5/2025 | 16/5/2025 | 2025-11-07 | 50000000
13 | CONSTRUCTION/ EQUIPPING OF FACULTY OF SCIENCE & TECHNOLOGY EDUCATION | 2025-03-02 | OPEN COMPETITIVE | 2025-03-03 | 21/5/2025 | 17/3/2025 | 28/4/2025 | 2025-05-05 | 22/5/2025 | 23/5/2025 | 2026-02-06 | 2025-03-06 | 24/2/2026 | 1800000000
14 | CONSTRUCTION/ EQUIPPING OF CUSTECH BUSINESS VENTURE | 2025-03-02 | OPEN COMPETITIVE | 2025-03-02 | 29/4/2025 | 17/2/2024 | 31/3/2025 | 2025-07-04 | 13/5/2025 | 14/5/2025 | 15/5/2025 | 16/5/2025 | 2025-11-07 | 50000000
15 | CONSTRUCTION/ EQUIPPING OF CUSTECH MICRO FINANCE BANK | 2025-03-02 | OPEN COMPETITIVE | 2025-03-02 | 29/4/2025 | 17/2/2025 | 31/3/2025 | 2025-07-04 | 13/5/2025 | 14/5/2025 | 15/5/2025 | 16/5/2025 | 25/7/2025 | 80000000
16 | CONSTRUCTION/ EQUIPPING OF SCIENCE LABORATORIES | 2025-03-02 | OPEN COMPETITIVE | 2025-03-02 | 29/4/2025 | 17/2/2025 | 31/3/2025 | 2025-07-04 | 13/5/2025 | 14/5/2025 | 15/5/2025 | 16/5/2025 | 2025-11-07 | 50000000
17 | CONSTRUCTION/ EQUIPPING OF CONVOCATION SQUARE (CUSTECH) | 2025-03-02 | OPEN COMPETITIVE | 2025-03-02 | 29/4/2025 | 17/2/2025 | 31/3/2025 | 2025-07-04 | 13/5/2025 | 14/5/2025 | 15/5/2025 | 16/5/2025 | 2025-08-08 | 100000000
18 | CONSTRUCTION OF CUSTECH INTERNAL ROAD |  | ON GOING | 2025-03-02 | 29/4/2025 |  |  | 2025-07-04 | 13/5/2025 | 14/5/2025 | 15/5/2025 | 16/5/2025 | 31/10/2025 | 2500000000
[5 empty] | CUSTECH PROCUREMENT PLANNING 2025 |  | (GOODS)
19 | PURCHASE OF 5 NOS OF MOTOR VEHICLE (BUSES & HILUX) |  | OPEN COMPETITIVE | 2025-03-02 | 29/4/2025 | 17/2/2025 | 31/3/2025 | 2025-07-04 | 13/5/2025 | 14/5/2025 | 15/5/2025 | 16/5/2025 | 13/6/2025 | 750000000
20 | PURCHASE OF 40 NOS. OF COMPUTERS |  | OPEN COMPETITIVE | 2025-03-02 | 29/4/2025 | 17/2/2025 | 31/3/2025 | 2025-07-04 | 13/5/2025 | 14/5/2025 | 15/5/2025 | 16/5/2025 | 13/6/2025 | 55000000
21 | PURCHASE OF 3NOS. PHOTOCOPING MACHINES |  | RESTRICTIVE TENDERING | 2025-01-02 | 5/3/2025 10/3/2025 | 17/2/2025 | 24/2/2025 | 2025-07-03 | 17/3/2025 | 18/3/2025 | 19/3/2025 | 20/3/2025 | 2025-03-04 | 8000000
22 | PURCHASE OF LIBRARY BOOKS & EQUIPMENT |  | OPEN COMPETITIVE | 2025-03-02 | 29/4/2025 | 17/2/2025 | 31/3/2025 | 2025-07-04 | 13/5/2025 | 14/5/2025 | 15/5/2025 | 16/5/2025 | 13/6/2025 | 50000000
23 | PURCHASE & INSTALLATION OF SECURITY GADGETS |  | RESTRICTIVE TENDERING | 2025-01-02 | 5/3/2025 10/3/2025 | 17/2/2025 | 24/2/2025 | 2025-07-03 | 17/3/2025 | 18/3/2025 | 19/3/2025 | 20/3/2025 | 2025-03-04 | 10000000
24 | PURCHASE OF FIRE ENGINES/FIGHTING EQUIPMENT & APPLIANCES |  | OPEN COMPETITIVE | 2025-03-02 | 29/4/2025 | 17/2/2025 | 31/3/2025 | 2025-07-04 | 13/5/2025 | 14/5/2025 | 15/5/2025 | 16/5/2025 | 13/6/2025 | 100000000
25 | PURCHASE & INSTALLATION OF 2 NOS. OF TRANSFORMER |  | OPEN COMPETITIVE | 2025-03-02 | 29/4/2025 | 17/2/2025 | 31/3/2025 | 2025-07-04 | 13/5/2025 | 14/5/2025 | 15/5/2025 | 16/5/2025 | 13/6/2025 | 1200000000
26 | PROCUREMENTS OF PLANT & EQUIPMENT |  | OPEN COMPETITIVE | 2025-03-02 | 29/4/2025 | 17/2/2025 | 31/3/2025 | 2025-07-04 | 13/5/2025 | 14/5/2025 | 15/5/2025 | 16/5/2025 | 13/6/2025 | 100000000
27 | PURCHASE OF 35 NOS. OF LAPTOP COMPUTERS |  | OPEN COMPETITIVE | 2025-03-02 | 29/4/2025 | 17/2/2025 | 31/3/2025 | 2025-07-04 | 13/5/2025 | 14/5/2025 | 15/5/2025 | 16/5/2025 | 13/6/2025 | 52500000
[5 empty] | CUSTECH PROCUREMENT PLANNING 2025 |  | (SERVICES)
28 | TRAINING & MANPOWER DEVELOPMENT |  | OPEN COMPETITIVE | 2025-03-02 | 29/4/2025 | 17/2/2025 | 31/3/2025 | 2025-07-04 | 13/5/2025 | 14/5/2025 | 15/5/2025 | 16/5/2025 | 13/6/2025 | 150000000