## Annual Procurement Plan
Procuring Entity Name | Ministry of Housing and Urban Development
Procurement Plan for year | 2026
Date Created
Comments
Estimated dates
Class | UNSPSC | Description | Ref No | Unit | Envisaged Quantity | Estimated Budget | Source of Funds | Prequalification (Y/N) | Procurement Method | Advert Publication Date | Award Date | Project Start Date | Project Completion Date
Works |  | proposed remodellong/construction of civic defence building at okene LGA kogi state |  | 1 | 1 | 1500000000 | Kogi state Government | Yes | Selective | 2025-12-24 | 2026-01-15 | 2026-01-26 | 2026-05-26
Works |  | proposed renovation and remodelling of NDLEA building at Okene LGA Kogi State |  | 1 | 1 | 1500000000 | Kogi state Government | Yes | selective | 2025-12-24 | 2026-01-15 | 2026-01-26 | 2026-05-26
Works |  | construction and renovation of central mosque at okene |  | 1 | 1 | 1500000000 | Kogi state Government | Yes | Selective | 2026-02-09 | 2026-04-26 | 2026-03-02 | 2026-07-02
Works |  | construction of Ministry of Housing and Urban development |  | 1 | 1 | 100000000 | Kogi state Government | Yes | Selective | 2026-03-16 | 2026-04-10 | 2026-04-20 | 2026-12-21
Works |  | construction of laboratry building for soil test in lokoja |  | 1 | 1 | 100000000 | Kogi state Government | Yes | Selective | 2026-05-04 | 2026-05-29 | 2026-06-08 | 2026-11-23
Works |  | construction of office building in 5 LGA across the kogi state |  | 5 | 5 | 1500000000 | Kogi state Government | Yes | Selective | 2026-07-06 | 2026-07-31 | 2026-08-10 | 2027-01-24