## Sheet1
ANNUAL PROCUREMENT PLAN FOR THE YEAR 2026
S/N | PROCUREMENT DESCRIPTION | PREPARATION OF DESIGN AND DRAWING | PROC METHOD | PREPARATION OF TENDER DOCUMENT DATE | BPP NO OBJECTION | ADVERTISEMENT DATE | TENDING OPENING DATE/TIME | EVALUATION DATE | APPROVAL OF EVALUATION REPORT | AWARD NOTIFICATION DATE | CONTRACT ACT SIGNING DATE | CONTRACT COMMENCEMENT | CONTRACT COMPLETION DATE | CONTRACT AMOUNT
1 | CONSTRUCTION OF URBAN WATER SCHEME - 1010012300600 | YES | OPEN COMPETITIVE BEEDING | 2026-03-03 | YES | 2026-04-03 | 6/3/2026/ 20/03/2026/ 2PM | 23/03/2026 | YES | 25/03/2026 | 27/03/2026 | 30/03/2026 | 30/04/2026 | 50000000
2 | REHABILITATION/REPAIR OF WATER SCHEME FOR BOTH URBAN AND SMALL TOWN-1010012300700 | YES | OPEN COMPETITIVE BEEDING | 2026-02-02 | YES | 2026-06-02 | 09/02/2026/ 23/02/2026 / 3PM | 25/02/2026 | YES | 26/02/2026 | 27/02/2026 | 28/02/2026 | 28/03/2026 | 400000000
3 | MAINTENANCE OF GREATER LOKOJA WATER SCHEME PHASE II- 10100123000900 | YES | OPEN COMPETITIVE BEEDING | 2026-02-02 | YES | 2026-06-02 | 09/02/2026/ 23/02/2026 / 3PM | 25/02/2026 | YES | 26/02/2026 | 27/02/2026 | 28/02/2026 | 28/03/2026 | 360000000
4 | COMPLETION OF 15 MOTORIZED AND HAND PUMP BOREHOLES IN THE STATE- 10100123001000 | YES | OPEN COMPETITIVE BEEDING | 2026-02-04 | YES | 2026-07-04 | 08/04/2026 / 27/04/2026 / 3:30PM | 29/04/2026 | YES | 30/04/2026 | 2026-01-05 | 2026-04-05 | 30/06/2026 | 360000000
5 | REHABILITATION/UPGRADING OF CENTRAL WATER PROJECT SCHEMES (OKENE, EKUKU, ADOGO, OGORI MANGOGO, ESOMI, EGGE, EDOGI, KUROKO-10100123001100 | YES | OPEN COMPETITIVE BEEDING | 2026-02-04 | YES | 2026-07-04 | 08/04/2026 / 27/04/2026 / 3:30PM | 29/04/2026 | YES | 30/04/2026 | 2026-01-05 | 2026-04-05 | 30/06/2026 | 360000000
6 | REHABILITATION/UPGRADING OF EASTERN WATER PROJECT SCHEME (EJULE, ODU, OKPAKILI, IDAH, ANKPA AGALIGA, IMMANE, AJAKA, ABEJUKOLO, ANYIGBA -10100123001200 | YES | OPEN COMPETITIVE BEEDING | 2026-02-04 | YES | 2026-07-04 | 08/04/2026 / 27/04/2026 / 3:30PM | 29/04/2026 | YES | 30/04/2026 | 2026-01-05 | 2026-04-05 | 30/06/2026 | 200000000
7 | REHABILITATION/UPGRADING OF WESTERN WATER SCHMES PROJECT( KABBA WATER PROJECT, ODIGI, MOPA, ISANLU, EGBE, AYEGUNLE GBEDE AND ONI-10100123001300 | YES | OPEN COMPETITIVE BEEDING | 2026-02-04 | YES | 2026-07-04 | 08/04/2026 / 27/04/2026 / 3:30PM | 29/04/2026 | YES | 30/04/2026 | 2026-01-05 | 2026-04-05 | 30/06/2026 | 350000000
8 | REHABILITATION AND RECTICULATION OF ISANLU WATER SCHEME- 10100123001500 | YES | OPEN COMPETITIVE BEEDING | 2026-02-04 | YES | 2026-07-04 | 08/04/2026 / 27/04/2026 / 3:30PM | 29/04/2026 | YES | 30/04/2026 | 2026-01-05 | 2026-04-05 | 30/06/2026 | 2000000000
9 | REPAIR/REPLACEMENT OF WARNOUT WATER SUPPLY EQUIPMENT (CHEMICAL SUPPLY INCLUSIVE)-1010012300600 | YES | OPEN COMPETITIVE BEEDING | 2026-03-03 | YES | 2026-04-03 | 6/3/2026/ 20/03/2026/ 2PM | 23/03/2026 | YES | 25/03/2026 | 27/03/2026 | 30/03/2026 | 30/04/2026 | 400000000
10 | EXPANSION AND RECTICULATION OF OKENE WATER WORKS-10100123001800 | YES | OPEN COMPETITIVE BEEDING | 2026-03-03 | YES | 2026-04-03 | 6/3/2026/ 20/03/2026/ 2PM | 23/03/2026 | YES | 25/03/2026 | 27/03/2026 | 30/03/2026 | 30/04/2026 | 200000000
11 | REHABILITATION OF MECHANICAL AND HYDRUALIC DREDGING OF OKENE WATER DAM- 10100123001900 | YES | OPEN COMPETITIVE BEEDING | 2026-03-03 | YES | 2026-04-03 | 6/3/2026/ 20/03/2026/ 2PM | 23/03/2026 | YES | 25/03/2026 | 27/03/2026 | 30/03/2026 | 30/04/2026 | 100000000
12 | REHABILITATION AND RECTICULATION OF AYEGUNLE GBEDE, IYAGBEDE, AYETOROGBEDE WATER SCHEME -10100123002000 | YES | OPEN COMPETITIVE BEEDING | 2026-01-06 | YES | 2026-04-06 | 8/6/2026 / 29/6/2026 / 3:30PM | 2026-01-07 | YES | 2026-03-07 | 2026-10-08 | 2026-12-08 | 2026-12-09 | 250000000
13 | RETICULATION AND METERING OF GREATER LOKOJA WATER SUPPLY SCHEME TO EXTENTION OF WATER TO FELELE, ZANGO AND FUL PERMANENT SITE-10100123002100 | YES | OPEN COMPETITIVE BEEDING | 2026-01-06 | YES | 2026-04-06 | 8/6/2026 / 29/6/2026 / 3:30PM | 2026-01-07 | YES | 2026-03-07 | 2026-10-08 | 2026-12-08 | 2026-12-09 | 500000000
14 | RESUSCITATION AND RETICULATION OF ANPKA WATER PROJECT- 10100123002200 | YES | OPEN COMPETITIVE BEEDING | 2026-01-06 | YES | 2026-04-06 | 8/6/2026 / 29/6/2026 / 3:30PM | 2026-01-07 | YES | 2026-03-07 | 2026-10-08 | 2026-12-08 | 2026-12-09 | 300000000
15 | REHABILITATION AND RETICULATION OF ADOGO WATER SCHEME-10100123002300 | YES | OPEN COMPETITIVE BEEDING | 2026-01-06 | YES | 2026-04-06 | 8/6/2026 / 29/6/2026 / 3:30PM | 2026-01-07 | YES | 2026-03-07 | 2026-10-08 | 2026-12-08 | 2026-12-09 | 200000000
16 | REHABILITATION AND RETICULATION OF IKUEHI, OBOROKE AND EIKA, OHIZEYIN WATER SCHEME - 10100123002400 | YES | OPEN COMPETITIVE BEEDING | 2026-01-06 | YES | 2026-04-06 | 8/6/2026 / 29/6/2026 / 3:30PM | 2026-01-07 | YES | 2026-03-07 | 2026-10-08 | 2026-12-08 | 2026-12-09 | 300000000
17 | NUT.5. WASH PROVIDE PORTABLE WATER SUPPLY IN PUBLIC PLACES TO ENHANCE SANITATION AND HYGIENE -10100124000100 | YES | OPEN COMPETITIVE BEEDING | 2026-03-03 | YES | 2026-04-03 | 6/3/2026/ 20/03/2026/ 2PM | 23/03/2026 | YES | 25/03/2026 | 27/03/2026 | 30/03/2026 | 30/04/2026 | 50000000
18 | REHABILITATION OF MOPA TOWNSHIP WATER SCHEME MOPA-10100124000300 | YES | OPEN COMPETITIVE BEEDING | 2026-05-10 | YES | 2026-08-10 | 12/10/2026 / 30/10/2026 / 3PM | 2026-02-11 | YES | 2026-07-11 | 2026-10-11 | 14/11/2026 | 15/12/2026 | 100000000
19 | PROVISION OF PORTABLE WATER TO AIYETEJU AGBAJOGUN AMURO-1010014000400 | YES | OPEN COMPETITIVE BEEDING | 2026-05-10 | YES | 2026-08-10 | 12/10/2026 / 30/10/2026 / 3PM | 2026-02-11 | YES | 2026-07-11 | 2026-10-11 | 14/11/2026 | 15/12/2026 | 30000000
20 | REHABILITATION OF ODO ERE WATER SCHEME -10100124000500 | YES | OPEN COMPETITIVE BEEDING | 2026-05-10 | YES | 2026-08-10 | 12/10/2026 / 30/10/2026 / 3PM | 2026-02-11 | YES | 2026-07-11 | 2026-10-11 | 14/11/2026 | 15/12/2026 | 50000000
21 | REHABILITATION OF WATER SCHEMES ACROSS KOGI STATE -101001240000800 | YES | OPEN COMPETITIVE BEEDING | 2026-02-02 | YES | 2026-06-02 | 09/02/2026/ 23/02/2026 / 3PM | 25/02/2026 | YES | 26/02/2026 | 27/02/2026 | 28/02/2026 | 28/03/2026 | 4000000000
22 | NUT.5 EMERGENCY SUPPORT WATER SUPPLY INTERVENTION IN EMERGENCY SETTING- | YES | OPEN COMPETITIVE BEEDING | 2026-03-03 | YES | 2026-04-03 | 6/3/2026/ 20/03/2026/ 2PM | 23/03/2026 | YES | 25/03/2026 | 27/03/2026 | 30/03/2026 | 30/04/2026 | 3864300
23 | NUT 5 WASH PROVIDE PORTABLE WATER IN SCHOOLS TO ENHANCE EFFECTIVE SANITATION AND HYGIENE ACROSS THE 21 LOCAL GOVERNMENT AREA IN KOGI STATE- 10100126000300 | YES | OPEN COMPETITIVE BEEDING | 2026-02-02 | YES | 2026-06-02 | 09/02/2026/ 23/02/2026 / 3PM | 25/02/2026 | YES | 26/02/2026 | 27/02/2026 | 28/02/2026 | 28/03/2026 | 75754300