## Sheet1
KOGI STATE MINISTRY OF EDUCATION ANNUAL PROCUREMENT/DISPOSAL PLAN 2026
S/N | CODE | PROJECT DESCRIPTION | CONTRACT CATEGORY | PROCUREMENT METHOD | BPP NO OBJECTION | ADVERTISEMENT | PREQUALIFICATION YES/NO | BID PREPARATION & SUBMISSION DATE | BID CLOSING | BID OPENING | BID EVALUATION REPORT DATE | AWARD DATE | CONTRACT SIGNING DATE | BUDGET AMOUNT | CONPLETION DATE
| 02100123002200 | CONSTRUCTION OF A BLOCK OF 5 OFFICES IN THE MOE HQ & A BLOCK OF 2 OFFICES EACH FOR THE AREA EVALUATORS OF EDUCATION (AEEs) in the 21 LGAs within one year | WORKS | OCB | 16/1/26 | 19/1/26 - 9/2/26 | YES | 20/ 01/26 - 09/02/26 | 09 - 02 - 26 12:00NOON | 09 - 02 - 26 12:15PM | 17 - 02 - 26 | 23 - 02 -26 | 26 - 02 - 26 | 150000000 | 28 - 05 - 26
| 02100123002400 | RENOVATION OF COMMUNITY SECONDARY SCHOOL, AGASA | WORKS | OCB | 16/1/26 | 19/1/26 - 9/2/26 | YES | 20 - 01 - 26 | 09 - 02 - 26/ 12:00NOON | 09 - 02 - 26 12:15PM | 17 - 02 - 26 | 23 - 02 -26 | 26 - 02 - 26 | 50000000 | 28 - 05 - 26
| 02100123002500 | RENOVATION OF COMMUNITY SECONDARY SCHOOL, OLOWA | WORKS | SELECTIVE TENDERING | 16/1/26 | 19/1/26 - 2/2/26 | YES | 20 - 01 - 26 | 09 - 02 - 26/ 12:00NOON | 09 - 02 - 26 12:15PM | 17 - 02 - 26 | 23 - 02 -26 | 26 - 02 - 26 | 11000000 | 28 - 05 - 26
| 05010223000100 | PROVISION OF VOCATIONAL SKILLS EQUIPMENT TO 21 CENTRES IN ALL THE 21 LGAs: (1) 42 SETS OF SEWING MACHINES (2) 42 SETS OF EMBRIDERY MACHINES (3) 42 WELDING MACHINES (4) 210 PIECES OF CLIPPERS FOR YOUTH & ADULT EDUCATION | SUPPLY | OCB | 2026-12-01 | 13/1/26 - 3/2/26 | YES | 14 -01- 26 | 03 - 02 - 26/ 12:00NOON | 03 - 02 - 26 12:15PM | 2026-11-02 | 17 - 02 - 26 | 20 - 02 - 26 | 50000000 | 20 - 03 - 26
| 05010423000100 | PROVISION OF MOTORCYCLES FOR 21 EDUCATION AREA EVALUATORS (INSPECTORS) IN 21 LGAs | SUPPLY | SELECTIVE TENDERING | 2026-12-01 | 13/1/26 - 3/2/26 | YES | 14 -01- 26 | 03 - 02 - 26/ 12:00NOON | 03 - 02 - 26 12:15PM | 2026-11-02 | 17 - 02 - 26 | 20 - 02 - 26 | 31500000 | 20 - 03 - 26
| 05030223000200 | INCLUSIVE EDUCATION/PROVISION OF LEARNING AIDS (BRAIDS TYPEWRITER, HEARING AID, WHEEL CHAIR & OTHERS) FOR SPECIAL EDUCATION (LEARNERS WITH SPECIAL NEED) IN 3 SPECIAL SCHOOLS AT IYALE, EGBE & ZANGO DAJI | SUPPLY | OCB | 2026-12-01 | 13/1/26 - 3/2/26 | YES | 14 -01- 26 | 03 - 02 - 26/ 12:00NOON | 03 - 02 - 26 12:15PM | 2026-11-02 | 17 - 02 - 26 | 20 - 02 - 26 | 100000000 | 20 - 03 - 26
| 05030423000100 | DEVELOPMENT OF E-LEARNING PROGRAMME (MOBILE APPLICATION) FOR TEACHERS, STUDENTS & PUPILS ACROSS THE STATE | SERVICES | QBS | 2026-12-01 | 13/1/26 - 3/2/26 | YES | 14 -01- 26 | 03 - 02 - 26/ 12:00NOON | 03 - 02 - 26 12:15PM | 2026-11-02 | 17 - 02 - 26 | 20 - 02 - 26 | 100000000 | 20 - 04 - 26
| 05030524000100 | ESTABLISHMENT OF GOVERNMENT DAY SECONDARY SCHOOL, ZANGO DAJI | WORKS | OCB | 16/1/26 | 19/1/26 - 9/2/26 | YES | 20 - 01 - 26 | 09 - 02 - 26/ 12:00NOON | 09 - 02 - 26 12:15PM | 17 - 02 - 26 | 23 - 02 -26 | 26 - 02 - 26 | 50000000 | 28 - 05 - 26
| 05040223000100 | SUPPLY OF SCIENCES LABORATORY EQUIPMENT TO PHYSICS, CHEMISTRY,BIOLOGY,AGRIC HOMEC & ICT LABS IN 21 GOVERNMENT SCIENCE SECONDARY SCHOOLS IN 21 LGAs | SUPPLY | OCB | 2026-12-01 | 13/1/26 - 3/2/26 | YES | 14 -01- 26 | 03 - 02 - 26/ 12:00NOON | 03 - 02 - 26 12:15PM | 2026-11-02 | 17 - 02 - 26 | 20 - 02 - 26 | 377964246 | 20 - 03 - 26
| 05040223000200 | SUPPLY OF 120,000 COPIES OF CUSTOMISED MATHEMATICS & ENGLISH TEXTBOOKS TO SECONDARY SCHOOLS | SUPPLY | OCB | 2026-12-01 | 13/1/26 - 3/2/26 | YES | 14 -01- 26 | 03 - 02 - 26/ 12:00NOON | 03 - 02 - 26 12:15PM | 2026-11-02 | 17 - 02 - 26 | 20 - 02 - 26 | 54000000 | 20 - 03 - 26
| 05040223000300 | PROVISION OF EQUIPMENT TO AIDGENDER ISSUES IN BASIC & POST BASIC EDUCATION; EQUIPMENT -126 KNITTING MACHINES, SEWING MACHINES, 132 DRYERS & 132 HAIR ROLLERS WHILE LEARNING MATERIALS ARE 300 WHITE BOARDS, 126 CARTONS OF MARKERS & 126 CARTONS OF CARD BOARD SHEETS | SUPPLY | OCB | 2026-12-01 | 13/1/26 - 3/2/26 | YES | 14 -01- 26 | 03 - 02 - 26/ 12:00NOON | 03 - 02 - 26 12:15PM | 2026-11-02 | 17 - 02 - 26 | 20 - 02 - 26 | 100000000 | 20 - 03 - 26
| 05040223000400 | PROVISION OF 25,000 COPIES OF NEW CURRICULUMS & TEACHER'S GUIDE ACROSS ALL SUBJECTSIN BASIC & POST BASIC LEVELS | SUPPLY | OCB | 2026-12-01 | 13/1/26 - 3/2/26 | YES | 14 -01- 26 | 03 - 02 - 26/ 12:00NOON | 03 - 02 - 26 12:15PM | 2026-11-02 | 17 - 02 - 26 | 20 - 02 - 26 | 100000000 | 20 - 03 - 26
| 0105050123000300 | RENOVATION/REMODELLING OF SECONDARY SCHOOLS ACROSS THE STATE (ALL) | WORKS | OCB | 16/1/26 | 19/1/26 - 9/2/26 | YES | 20 - 01 - 26 | 09 - 02 - 26/ 12:00NOON | 09 - 02 - 26 12:15PM | 17 - 02 - 26 | 23 - 02 -26 | 26 - 02 - 26 | 2030414522 | 28 - 05 - 26
| 05050123000500 | ESTABLISHMENT OF EJIGBO COMMUNITY SECONDARY SCHOOL | WORKS | OCB | 16/1/26 | 19/1/26 - 9/2/26 | YES | 20 - 01 - 26 | 09 - 02 - 26/ 12:00NOON | 09 - 02 - 26 12:15PM | 17 - 02 - 26 | 23 - 02 -26 | 26 - 02 - 26 | 30000000 | 28 - 05 - 26
| 05050123000600 | RENOVATION/UPGRADING OF EXISTING TECHNICAL SCHOOLS (ANKPA, IDAH, OBOROKE & MOPA) | WORKS | OCB | 16/1/26 | 19/1/26 - 9/2/26 | YES | 20 - 01 - 26 | 09 - 02 - 26/ 12:00NOON | 09 - 02 - 26 12:15PM | 17 - 02 - 26 | 23 - 02 -26 | 26 - 02 - 26 | 150000000 | 28 - 05 - 26
| 05050123000700 | RENOVATION & EXPANSION LEARNING ENVIRONMENT IN 42 SCHOOLS 2 PER LGA (GYB LEGACY/MODEL SCH. PROJECT) | WORKS | OCB | 16/1/26 | 19/1/26 - 9/2/26 | YES | 20 - 01 - 26 | 09 - 02 - 26/ 12:00NOON | 09 - 02 - 26 12:15PM | 17 - 02 - 26 | 23 - 02 -26 | 26 - 02 - 26 | 100000000 | 28 - 05 - 26
| 05050123000800 | RENOVATION OF ABDULAZIZ ATTA MEMORIAL COLLEGE (AAMCO), OKENE | WORKS | OCB | 16/1/26 | 19/1/26 - 9/2/26 | YES | 20 - 01 - 26 | 09 - 02 - 26/ 12:00NOON | 09 - 02 - 26 12:15PM | 17 - 02 - 26 | 23 - 02 -26 | 26 - 02 - 26 | 100000000 | 28 - 05 - 26
| 05050123000900 | RENOVATION OF GOVERNMENT SECONDARY SCHOOL, OGAMINANA | WORKS | OCB | 16/1/26 | 13/1/26 - 3/2/26 | YES | 20 - 01 - 26 | 09 - 02 - 26/ 12:00NOON | 09 - 02 - 26 12:15PM | 17 - 02 - 26 | 23 - 02 -26 | 26 - 02 - 26 | 100000000 | 28 - 05 - 26
| 05050123001000 | RENOVATION OF OKENE SECONDARY SCHOOL | WORKS | OCB | 16/1/26 | 19/1/26 - 9/2/26 | YES | 20 - 01 - 26 | 09 - 02 - 26/ 12:00NOON | 09 - 02 - 26 12:15PM | 17 - 02 - 26 | 23 - 02 -26 | 26 - 02 - 26 | 75000000 | 28 - 05 - 26
| 05050123001100 | PROCUREMENT OF EQUIPMENT TO GOVERNMENT TECHNICAL SCHOOLS WORKSHOP: AUTO-MECHANIC W/SHOP, WELDING & FABRICATION W/SHOP, CARPENTRY & JOINERY W/SHOP AND OTHERS | SUPPLY | OCB | 2026-12-01 | 13/1/26 - 3/2/26 | YES | 14 -01- 26 | 03 - 02 - 26/ 12:00NOON | 03 - 02 - 26 12:15PM | 2026-11-02 | 17 - 02 - 26 | 20 - 02 - 26 | 100000000 | 20 - 03 - 26
| 05050124000100 | RENOVATION OF ECWA SECONDARY SCHOOL, MOPA | WORKS | OCB | 16/1/26 | 19/1/26 - 9/2/26 | YES | 20 - 01 - 26 | 09 - 02 - 26/ 12:00NOON | 09 - 02 - 26 12:15PM | 17 - 02 - 26 | 23 - 02 -26 | 26 - 02 - 26 | 20000000 | 28 - 05 - 26
| 05050125001700 | RENOVATION OF GOVERNMENT SECONDARY SCHOOL (GSS), ABEJUKOLO | WORKS | OCB | 16/1/26 | 19/1/26 - 9/2/26 | YES | 20 - 01 - 26 | 09 - 02 - 26/ 12:00NOON | 09 - 02 - 26 12:15PM | 17 - 02 - 26 | 23 - 02 -26 | 26 - 02 - 26 | 50000000 | 28 - 05 - 26
| 05050323000200 | UPGRADING OF SCIENCE LABORATORY IN ALL SPECIAL SCIENCE SECONDARY SCHOOLS ACROSS THE STATE | SUPPLY | OCB | 2026-12-01 | 13/1/26 - 3/2/26 | YES | 14 -01- 26 | 03 - 02 - 26/ 12:00NOON | 03 - 02 - 26 12:15PM | 2026-11-02 | 17 - 02 - 26 | 20 - 02 - 26 | 65000000 | 20 - 03 - 26
| 05050423000200 | CONSTRUCTION OF VIP TOILETS & SANITATION FOR SCHOOLS ACROSS THE STATE | WORKS | OCB | 16/1/26 | 19/1/26 - 9/2/26 | YES | 20 - 01 - 26 | 09 - 02 - 26/ 12:00NOON | 09 - 02 - 26 12:15PM | 17 - 02 - 26 | 23 - 02 -26 | 26 - 02 - 26 | 28678975 | 28 - 05 - 26
| 05050523000200 | PROCUREMENT & INSTALLATION OFCCTV CAMERA TO 3 SCHOOLS PER LGA IN THE STATE (4 CCTV CAMERA IN 63 SCHOOLS) | SUPPLY | SELECTIVE TENDERING | 2026-12-01 | 13/1/26 - 3/2/26 | YES | 14 -01- 26 | 03 - 02 - 26/ 12:00NOON | 03 - 02 - 26 12:15PM | 2026-11-02 | 17 - 02 - 26 | 20 - 02 - 26 | 25200000 | 20 - 03 - 26
| 05060123000100 | ACQUISITION OF 15 PLOTS OF LAND FOR EDUCATION RESOURCE CENTRE | SUPPLY | OCB | 2026-12-01 | 13/1/26 - 3/2/26 | YES | 14 -01- 26 | 03 - 02 - 26/ 12:00NOON | 03 - 02 - 26 12:15PM | 2026-11-02 | 17 - 02 - 26 | 20 - 02 - 26 | 30000000 | 20 - 03 - 26
| 05060323000100 | UPGRADING OF FACILITIES AT EDUCATION MANAGEMENT INFORMATION SYSTEM UNIT (EMIS), MOE, HEADQUARTERS | SUPPLY | RFQ | 2026-12-01 | 13/1/26 - 3/2/26 | YES | 14 -01- 26 | 03 - 02 - 26/ 12:00NOON | 03 - 02 - 26 12:15PM | 2026-11-02 | 17 - 02 - 26 | 20 - 02 - 26 | 16000000 | 20 - 03 - 26
| 05100123000100 | PROCUREMENT OF SPORTS EQUIPMENT IN SCHOOLS | SUPPLY | OCB | 2026-12-01 | 13/1/26 - 3/2/26 | YES | 14 -01- 26 | 03 - 02 - 26/ 12:00NOON | 03 - 02 - 26 12:15PM | 2026-11-02 | 17 - 02 - 26 | 20 - 02 - 26 | 30000000 | 20 - 03 - 26
| 010100123003300 | RENOVATION, SINKING OF BOREHOLD & PROVISION OF DESK IN GOVERNMENT GIRLS MODEL SECONDARY SCHOOL, OGBONICHA | WORKS | OCB | 16/1/26 | 19/1/26 - 9/2/26 | YES | 20 - 01 - 26 | 09 - 02 - 26/ 12:00NOON | 09 - 02 - 26 12:15PM | 17 - 02 - 26 | 23 - 02 -26 | 26 - 02 - 26 | 75000000 | 28 - 05 - 26
| 011100123004600 | PROVISION OF 2 LAPTOPS, 1 PRINTER & OTHER ACCESSORIES FOR EACH DEPARTMENT IN THE MINISTRY OF EDUCATION HEADQUARTER | SUPPLY | OCB | 2026-12-01 | 13/1/26 - 3/2/26 | YES | 14 -01- 26 | 03 - 02 - 26/ 12:00NOON | 03 - 02 - 26 12:15PM | 2026-11-02 | 17 - 02 - 26 | 20 - 02 - 26 | 30000000 | 20 - 03 - 26
| 011100123004800 | ESTABLISHMENT OF ONE (1 NO) PILOT ICT CENTRE IN ONE SECONDARY SCHOOL PER LOCAL GOVERNMENT | SUPPLY | OCB | 2026-12-01 | 13/1/26 - 3/2/26 | YES | 14 -01- 26 | 03 - 02 - 26/ 12:00NOON | 03 - 02 - 26 12:15PM | 2026-11-02 | 17 - 02 - 26 | 20 - 02 - 26 | 100000000 | 20 - 03 - 26
| 05020326000100 | NUT 1 SBPS ESTABLISHMENT OF 90 SCHOOL GARDEN ACROSS THE STATE WITH THE USE OF SIMPLE FARM TOOLS TO COMPLEMENT SCHOOL FEEDING PROGRAMME | SUPPLY | SELECTIVE TENDERING | 2026-12-01 | 13/1/26 - 3/2/26 | YES | 14 -01- 26 | 03 - 02 - 26/ 12:00NOON | 03 - 02 - 26 12:15PM | 2026-11-02 | 17 - 02 - 26 | 20 - 02 - 26 | 20.350,000.00 | 20 - 03 - 26
| 005050126001700 | CONSTRUCTION OF CLASSROOMS IN SELECTED NUMBER OF SCHOOLS ACROSS THE STATE (AGILE PROJECT) | WORKS | OCB | 16/1/26 | 19/1/26 - 9/2/26 | YES | 20 - 01 - 26 | 09 - 02 - 26/ 12:00NOON | 09 - 02 - 26 12:15PM | 17 - 02 - 26 | 23 - 02 -26 | 26 - 02 - 26 | 30616282000 | 28 - 05 - 26
| 005050126001800 | RENOVATION OF CLASSROOMS IN SELECTED NUMBER OF SCHOOLS ACROSS THE STATE (AGILE PROJECT) | WORKS | OCB | 16/1/26 | 19/1/26 - 9/2/26 | YES | 20 - 01 - 26 | 09 - 02 - 26/ 12:00NOON | 09 - 02 - 26 12:15PM | 17 - 02 - 26 | 23 - 02 -26 | 26 - 02 - 26 | 28022380421 | 28 - 05 - 26