## Sheet1
KOGI STATE UNIVERSAL BASIC EDUCATION BOARD 2026 ANNUAL PROCUREMENT AND DISPOSAL PLAN
S/N | PROJECT DESCRIPTION | PREPARATION OF DESIGN & DRAWING | PROCUREMENTMETHOD | PREPARATION OF TENDER DOCUMENTS DATE | BPP NO OBJECTION | ADVERTISEMENT DATE | TENDER CLOSING DATE | TENDER OPENING DATE | EVALUATION DATE | APPROVAL OF EVALUATION REPORT | AWARD NOTIFICATION DATE | CONTRACT SIGNING DATE | CONTRACT COMMENCEMENT DATE | CONTRACT COMPLETION DATE | PROPOSED BUDGETARY PROVISION (N)
| CONSTRUCTION OF 3 CLASSROOM WITH PRINCIPAL OFFICE & STORE | 2026-09-02 | OCB | 2026-11-02 | 13/2/2026 | 16/2/26 - 16/3/26 | 16/3/26 | 16 - 3 - 26 /12:10PM | 30/3/26 | 2026-01-04 | 2026-06-04 | 2026-09-04 | 13/4/26 | 13/7/26 | 235900505
| CONSTRUCTION OF 2 ECCDE CLASSROOM WITH CHILDREN PLAYGRAND & WATER | 2026-09-02 | OCB | 2026-11-02 | 13/2/2026 | 16/2/26 - 16/3/26 | 16/3/26 | 16 - 3 - 26 /12:10PM | 30/3/26 | 2026-01-04 | 2026-06-04 | 2026-09-04 | 13/4/26 | 13/7/26 | 185001157
| CONSTRUCTION OF 2 CLASSROOM | 2026-09-02 | OCB | 2026-11-02 | 13/2/2026 | 16/2/26 - 16/3/26 | 16/3/26 | 16 - 3 - 26 /12:10PM | 30/3/26 | 2026-01-04 | 2026-06-04 | 2026-09-04 | 13/4/26 | 13/7/26 | 531300210
| PERIMETER FENCE: CONSTRUCTION OF FENCE | 2026-09-02 | OCB | 2026-11-02 | 13/2/2026 | 16/2/26 - 16/3/26 | 16/3/26 | 16 - 3 - 26 /12:10PM | 30/3/26 | 2026-01-04 | 2026-06-04 | 2026-09-04 | 13/4/26 | 13/7/26 | 133045620.9
| CONSTRUCTION OF VIP TOILET | 2026-09-02 | SELECTIVE TENDERING | 2026-11-02 |  | 16/2/26 - 2/3/26 | 2026-02-03 | 2 - 3 - 26 /12:10PM | 2026-09-03 | 2026-11-03 | 13/3/26 | 16/3/26 | 19/3/26 | 30/4/26 | 18150435.9
| RENOVATION OF CLASSROOMS | 2026-09-02 | OCB | 2026-11-02 | 13/2/2026 | 16/2/26 - 16/3/26 | 16/3/26 | 16 - 3 - 26 /12:10PM | 30/3/26 | 2026-01-04 | 2026-06-04 | 2026-09-04 | 13/4/26 | 15/6/26 | 2562181221
| PROVISION OF FUNITURES | 2026-09-02 | OCB | 2026-11-02 | 13/2/2026 | 16/2/26 - 16/3/26 | 16/3/26 | 16 - 3 - 26 /12:10PM | 30/3/26 | 2026-01-04 | 2026-06-04 | 2026-09-04 | 13/4/26 | 15/6/26 | 1055789802.11
| DRILLING OF MOTORIZED BOREHOLE | 2026-09-02 | OCB | 2026-11-02 |  | 16/2/26 - 2/3/26 | 2026-02-03 | 2 - 3 - 26 /12:10PM | 2026-09-03 | 2026-11-03 | 13/3/26 | 16/3/26 | 19/3/26 | 30/4/26 | 182421324.6
| TRAINING OF CENTERS FACILITATORS ON NEEDED INTEGRATION SKILL FOR REINTEGRATION OOSC |  | CQS | 2026-11-02 |  |  |  |  | 2026-09-03 | 2026-11-03 | 13/3/26 | 16/3/26 | 19/3/26 | 23/4/26 | 12000000
| PROCUREMENT OF HP 19 LAPTOP FOR DATA COLLATION & UPLOADS |  | RFQ | 2026-11-02 |  |  |  |  | 2026-09-03 | 2026-11-03 | 13/3/26 | 16/3/26 | 19/3/26 | 16/4/26 | 18510272.19
| PROCUREMENT OF HP 1 DESKTOP FOR OFFICE DESK WORK |  | DIRECT CONTRACTING | 2026-11-02 |  |  |  |  | 2026-09-03 | 2026-11-03 | 13/3/26 | 16/3/26 | 19/3/26 | 16/4/26 | 798850.8
| MAINTENANCE OF DATA PLATFORM |  | SINGLE SOURCING | 2026-11-02 |  |  |  |  | 2026-09-03 | 2026-11-03 | 13/3/26 | 16/3/26 | 19/3/26 | 16/4/26 | 1880605.1
| PROCUREMENT OF MOTOCYCLES |  | DIRECT CONTRACTING | 2026-11-02 |  |  |  |  | 2026-09-03 | 2026-11-03 | 13/3/26 | 16/3/26 | 19/3/26 | 16/4/26 | 2580952.87
| PROCUREMENT OF SAMSUNG GALAXY TAB A 10"/5G/8GBRAM/1TBROM/LATEST ANDROID VERSION & POWERBANKS FOR LGEA PLANNING & EMIS STAFF |  | RFQ | 2026-11-02 |  |  |  |  | 2026-09-03 | 2026-11-03 | 13/3/26 | 16/3/26 | 19/3/26 | 16/4/26 | 10998660.36
| PROCUREMENT OF OPERATIONAL VEHICLE |  | RFQ | 2026-11-02 |  |  |  |  | 2026-09-03 | 2026-11-03 | 13/3/26 | 16/3/26 | 19/3/26 | 16/4/26 | 13501362.1
| PROCUREMENT OF HP LAPTOP ELITEBOOK 1040 G9 TOUCH SCREEN CORE i7 - 16GBRAM/1TB SSD/WINDOWS 11 PRO + BAG FOR PLANNING & EMIS STAFF OF SUBEB |  | RFQ | 2026-11-02 |  |  |  |  | 2026-09-03 | 2026-11-03 | 13/3/26 | 16/3/26 | 19/3/26 | 16/4/26 | 20150206.56
| PROCUREMENT OF HP LAPTOP ELITEBOOK 840, TOUCH SCREEN CORE i5 - 8GB RAM, 512GB SSD, WINDOWS 11 PRO + BAG FOR LGEA PLANNING & EMIS STAFF |  | RFQ | 2026-11-02 |  |  |  |  | 2026-09-03 | 2026-11-03 | 13/3/26 | 16/3/26 | 19/3/26 | 16/4/26 | 18610940.74
| PROCUREMENT OF OPERATIONAL VEHICLE(S) FOR MONITORING & EVALUATION |  | RFQ | 2026-11-02 |  |  |  |  | 2026-09-03 | 2026-11-03 | 13/3/26 | 16/3/26 | 19/3/26 | 16/4/26 | 27104536.8
| MONITORYING & TRACKING OF NEW CURRICULUM IMPLEMENTATION ACROSS THE 21 LGAs |  | CQS | 2026-11-02 |  |  |  |  | 2026-09-03 | 2026-11-03 | 13/3/26 | 16/3/26 | 19/3/26 | 16/4/26 | 9495603.2
| SYSTEM SOFTWARE & HARDWARE UPGRADE & MAINTENANCE |  | CQS | 2026-11-02 |  |  |  |  | 2026-09-03 | 2026-11-03 | 13/3/26 | 16/3/26 | 19/3/26 | 16/4/26 | 5000000
| CONDUCT OF ICT TRAINING FOR SUBEB & ICT STAFF |  | CQS | 2026-11-02 |  |  |  |  | 2026-09-03 | 2026-11-03 | 13/3/26 | 16/3/26 | 19/3/26 | 16/4/26 | 14304000.4