## Sheet1
S/N | PROJECT DESCRIPTION | PREPARATION OF DESIGN & DRAWING | PROC. METHOD | PREPATION OF TENDER DOCUMENTS DATE | BPP NO OBJECTION | ADVERTISEMENT DATE | TENDER CLOSING & OPENING DATE/TIME | EVALUTION DATE | APPROVAL OF EVALUATION REPORT | AWARD NOTIFICATION ON DATE | CONTRACT SIGNING DATE | CONTRACT COMMENCE | CONTRACT COMPLETION DATE | BUDGET AMOUNT
1 | PROVISION OF OFFICE EQUIPMENT: 2NO COMPUTERS, 2 NO PRINTERS ETC FOR LAND DEVELOPMENT BOARD |  | GOODS | 2026-03-02 | 2026-06-02 | 2026-09-02 | 2026-02-03 | 2026-03-03 | 2026-05-03 | 2026-10-03 | 2026-09-04 | 2026-09-04 | 30/4/26 | 20000000
2 | ESTABLISHMENT OF 4000 HECTARES OF OIL PALM PLANTATION AT ALOMA. |  | WORKS | 2026-01-06 | 2025-04-06 | 2026-08-06 | 29/6/26 | 30/6/26 | 2026-03-07 | 2026-10-07 | 2026-10-08 | 2026-11-08 | 2026-10-11 | 40000000
3 | REHABILITATION OF EXISTING OIL PALM PROJECT AT ALLOMA, KABBA AND ACHARU(FSTP) |  | WORKS | 2026-06-07 | 2026-09-07 | 13/7/26 | 27/7/26 | 28/7/26 | 30/7/26 | 2026-06-08 | 2026-03-09 | 2026-04-09 | 2026-03-12 | 60000000
4 | ESTABLISHMENT /CONSTRUCTION OF CASSAVA, RICE, CASHEW AND OTHER STABLE CROPS CENTRE INCLUDING BOREHOLES AND OVERHEAD TANKS BY IFAD ASSISTANED VALUE CHAIN DEVELOPMENT PROGRAMME |  | WORKS | 2026-04-08 | 2026-07-08 | 2026-11-08 | 2026-01-09 | 2026-02-09 | 2026-07-09 | 14/9/26 | 13/10/26 | 13/10/26 | 2027-12-01 | 100,000,00
5 | SUPPLY OF SIMPLE FARM TOOLS FOR SCHOOLS AND HOME GARDENS ( HOE, CUTLASS, WHEELBARROW) |  | GOODS | 2026-09-03 | 2026-12-03 | 16/3/26 | 2026-06-04 | 2026-07-04 | 2026-09-04 | 16/4/26 | 14/5/26 | 14/5/26 | 2026-04-06 | 30000000
6 | ESTABLISHMENT 3 MEGA CASSAVA MILLING PROCESSING CENTRE(ONE IN EACH SENETORIAL DISTRICT)(FSTP) |  | WORKS | 2026-02-06 | 2026-05-06 | 2026-08-06 | 29/6/2026 | 30/6/26 | 2026-02-07 | 2026-08-07 | 2026-10-08 | 2026-11-08 | 2026-12-11 | 100000000
7 | CONSTRUCTION OF SPECIAL AGRO INDUSTRIAL PROCESSING ZONES. SAPZ II |  | WORKS | 2026-05-08 | 2026-10-08 | 2025-12-08 | 2026-02-09 | 2026-03-09 | 2026-07-09 | 14/9/25 | 14/10/26 | 15/10/26 | 18/1/2027 | 500000000
8 | ESTABLISHMENT OF 3NO GARRI PROCESSING CENTRE IN EACH SENATORIAL DISTRICT(WOMEN IN AGRICULTURE) |  | WORKS | 13/4/2026 | 16/4/26 | 20/4/26 | 2026-11-05 | 2026-12-05 | 15/5/26 | 22/5/26 | 22/6/26 | 23/6/26 | 24/9/26 | 300000000
9 | PROCUREMENT OF 30NO MINI MILLING PROCESSING MACHINE IN EACH SENATORIAL DISTRICT FOR RURAL FARMERS |  | GOODS | 16/3/2026 | 19/3/26 | 23/3/26 | 15/4/26 | 16/4/26 | 23/4/26 | 25/5/26 | 26/5/26 | 27/5/26 | 17/6/26 | 100000000
10 | PURCHASE OF 50 NOS OF 6 HORSE POWER SOLAR WATER PUMP FOR IRRIGATION SCHEME |  | GOODS | 2026-03-02 | 2026-06-02 | 2026-10-02 | 2026-03-03 | 2026-04-03 | 2026-09-03 | 16/3/26 | 16/4/26 | 17/4/26 | 2026-08-05 | 50000000
11 | REHABILITATION OF GREEN HOUSE FARMING SYSTEM AT OSARA |  | WORKS | 2026-01-07 | 2026-06-07 | 2026-08-07 | 29/7/26 | 30/7/26 | 2026-03-08 | 2026-10-08 | 2026-10-09 | 2026-11-09 | 2026-02-10 | 100000000
12 | PURCHASING OF 1000NOS WATER PUMPING MACHINES TO AID DRYSEASONING FARMING FOR YOUTH IN AGRICULTURE |  | GOODS | 2026-04-05 | 2026-07-05 | 2026-11-05 | 2026-01-06 | 2026-02-06 | 2026-05-06 | 2026-11-06 | 2026-06-07 | 2026-07-07 | 28/7/26 | 150000000
13 | ESTABLISHMENT OF 5000 METRIC TONNES SILOS IN 3 SENATORIAL DISTRICTS FOR POST HARVEST LOSSES |  | WORKS | 2026-06-04 | 2026-09-04 | 13/4/26 | 2026-04-05 | 2026-05-05 | 2026-08-05 | 15/5/26 | 2026-08-06 | 2026-09-06 | 2026-09-09 | 100000000
14 | REHABILITATION OF FISH HATCHERIES COMPLEX AIYETORO-GBEDE |  | WORKS | 2026-11-05 | 14/5/26 | 18/5/26 | 2026-02-06 | 2026-03-06 | 2026-08-06 | 15/6/26 | 15/7/26/ | 16/7/26 | 19/10/26 | 20000000
15 | PROCUREMENT OF FISHING GEARS (NET,CANOE,BOAT,TRAWER FOR FISHERMEN IN 9 LGAs) |  | GOODS | 2026-09-03 | 2026-12-03 | 18/3/26 | 2026-08-04 | 2026-09-04 | 13/4/26 | 20/4/26 | 20/5/26 | 21/5/26 | 2026-11-06 | 20000000
16 | PROVISION OF AGRICULTURAL EQUIPMENT(RIGGER HARROWS,POWER TILLERS,HARVESTERS,PLANTERS) BY KOGI STATE AGRICULTURAL DEVELOPMENT PROJECT (ADP) |  | GOODS | 2026-06-04 | 2026-09-04 | 13/4/26 | 2026-04-05 | 2026-05-05 | 2026-08-05 | 15/5/26 | 15/6/26 | 16/6/26 | 2026-07-07 | 200,000,00
17 | PROCUREMENT OF 10 N0S TRACTORS FOR AGRICULTURAL MECHANIZATION IN THE STATE |  | GOODS | 20/4/26 | 23/4/26 | 27/4/26 | 18/5/2026 | 19/5/26 | 22/5/26 | 29/5/26 | 29/6/26 | 30/6/26 | 20/7/26 | 1500000000
18 | PROCUREMENT OF 3 NOS TRESHER AND,3 NOS AND PLANTERS IN THE STATE |  | GOODS | 2026-09-02 | 2026-12-02 | 16/2/26 | 2026-09-03 | 2026-10-03 | 13/3/26 | 20/3/26 | 20/4/26 | 21/4/26 | 2026-04-05 | 100000000
19 | PROCUREMENT OF POWER TILLERS AND HARVESTERS INCLUDING FERTLIZERS, IMPROVED SEEDS TO BOOST FOOD SECURITY AND SAFE FUNCTIONING OF FOOD SUPPLY CHAINS FOR POOR HOUSEHOLDS (CARES) |  | GOODS | 2026-04-05 | 2026-07-05 | 2026-11-05 | 2026-01-06 | 2026-02-06 | 2026-05-06 | 2026-12-06 | 13/7/26 | 14/7/26 | 2026-04-08 | 6000000000
20 | PROCUREMENT OF 70NO MOTORIZED SPRAYER TO IMPROVE/SUPPORT FOR LIVELIHOOD AGRICULTURAL ACTIVITIES ACROSS THE STATE |  | GOODS | 2026-06-04 | 2026-09-04 | 13/4/26 | 2026-04-05 | 2026-05-05 | 2026-08-05 | 15/5/26 | 15/6/26 | 16/6/26 | 2026-07-07 | 100000000
21 | PROCUREMENT OF 1 NO ESCRAVATORS 1 NOS LOW BED, 3 NOS CART( D8K )BULDOZER AND PROVISION TRUST FUND MODEL TO FARMERS FOR UNDER COMMERCIAL AGRICULTURAL SCHEME FSP |  | GOODS | 2026-02-02 | 2026-05-02 | 2026-09-02 | 2026-02-03 | 2026-03-03 | 2026-06-03 | 13/3/26 | 13/4/26 | 14/4/26 | 2026-05-05 | 1000000000
22 | REFURBLISHING/REPAIRS OF VEHICLES,TRACTORS AND FOR FADAMA |  | WORKS | 2026-04-05 | 2026-07-05 | 14/5/26 | 2026-01-06 | 2026-02-06 | 2026-05-06 | 2026-12-06 | 13/7/26 | 14/7/26 | 14/10/26 | 60000000
23 | ESTABLISHMENT OF ACQUA CULTURE, CLUSTERS TO EMPOWER WOMEN AND YOUTH IN KOGI STATE (FSTP) |  | WORKS | 2026-08-06 | 2026-11-06 | 15/6/26 | 2026-06-07 | 2026-07-07 | 2026-10-07 | 17/7/26 | 17/8/26 | 18/8/26 | 18/11/26 | 500000000
24 | PROCUREMENT OF 21 COMPUTERS AND ICT GADGETS FOR FARMERS DATA BANK (21 LGAS) |  | GOODS | 13/4/26 | 16/4/26 | 20/4/26 | 2026-11-05 | 2026-12-05 | 15/5/26 | 22/5/26 | 22/6/26 | 23/6/26 | 14/7/26 | 40000000
25 | CONSTRUCTION OF 3NOS OF OFFICE BUILDINGS IN COLLEGE OF AGRICULTURE TRAINNING INSTITUTE,OCHAJA |  | WORKS | 2026-08-07 | 13/7/26 | 15/7/26 | 2026-05-08 | 2026-06-08 | 2026-10-08 | 17/8/26 | 2026-10-09 | 2026-11-08 | 2026-11-12 | 50000000
26 | RENOVATION/ EQUIPPING OF AGRO-ALLIED COMPANY LIMITED OFFICE BUILDING AT LOKOJA |  | WORKS | 16/2/26 | 19/2/26 | 23/2/2026 | 16/3/26 | 17/3/26 | 20/3/26 | 27/3/26 | 27/4/26 | 28/4/26 | 28/7/26 | 20000000
27 | REHABILITATION OF FERTILIZER STORE AT LOKOJA |  | WORKS | 2026-06-04 | 2026-09-04 | 13/4/26 | 2026-04-05 | 2026-05-05 | 2026-08-05 | 15/5/26 | 15/6/26 | 16/6/26 | 16/10/26 | 2000000
28 | RENOVATION OF MINISTRY OF AGRICULTURE,FOOD AND SECURITY OFFICE |  | WORKS | 2026-09-03 | 2026-12-03 | 16/3/26 | 2026-06-04 | 2026-07-04 | 2026-10-04 | 17/4/26 | 18/5/26 | 19/5/26 | 19/8/26 | 100000000
29 | ESTABLISHMENT OF 50 NO VEGETABLE HOME GARDENS IN EACH LOCAL GOVERNMENT OF THE STATE (CLIMATE CHANGE)(FSTP) |  | WORKS | 2026-02-03 | 2026-05-03 | 2026-09-03 | 30/3/26 | 31/3/26 | 2026-03-04 | 2026-10-04 | 2026-11-05 | 2026-12-05 | 2026-12-08 | 50000000
30 | ESTABLISHMENT OF CLIMATE SMART AGRICULTURAL CENTRE (SOIL AND WATER MANAGEMENT) FOR WOMEN AND YOUTH IN EACH OF THE SENATORIAL DISTRICT |  | WORKS | 16/2/26 | 19/2/26 | 23/2/24 | 16/3/26 | 17/3/26 | 20/3/26 | 27/3/26 | 27/4/26 | 28/4/26 | 28/7/26 | 100000000
31 | PROCUREMENT OF CLIMATE CHANGE MANGEMENT EQUIPMENT FOR SUSTAINABLE AGRICULTURE IN KOGI STATE |  | GOODS | 2026-09-02 | 2026-12-02 | 16/2/26 | 2026-09-03 | 2026-10-03 | 13/3/26 | 20/3/26 | 20/4/26 | 21/4/26 | 2026-12-05 | 100000000
32 | ESTABLISHMENT OF DEMONSTRATION FARM CENTRE USING ORGANIC FARMING FOR AGRO-ECOLOGY IN 21 LGAs |  | GOODS | 16/2/2026 | 19/2/26 | 23/2/26 | 19/3/26 | 20/3/26 | 23/3/26 | 30/3/26 | 30/4/26 | 2026-01-05 | 22/5/26 | 100000000
33 | ESTABLISHMENT OF 100 HECTARES OF FARM CLUSTER FOR YOUTH IN EACH SENATORIAL DISTRICT |  | GOODS | 20/4/26 | 27/4/26 | 18/5/2026 | 19/5/2026 | 22/5/26 | 29/5/26 | 29/6/26 | 30/6/26 | 2026-01-07 | 22/7/26 | 100,000,00
34 | PROVISION OF STARTER PACKS TO 90 SMALL HOLDERS RUMINANT FARMER (SHEEP, GOATS, CONCENTRATES, AND MEDICALS) 30 FARMERS FOR EACH OF THE THREE SENATORIAL ZONE |  | GOODS | 2026-10-08 | 13/8/26 | 17/8/26 | 2026-07-09 | 2026-08-09 | 2026-11-09 | 18/9/26 | 19/10/26 | 20/10/26 | 2026-10-11 | 5482500
35 | ESTABLISHMENT OF SPECIAL FARMS FOR FRUITS, VEGETABLES AND EDIBLE MUSHROOMS. |  | WORKS | 2026-09-03 | 2026-12-03 | 16/3/26 | 2026-06-04 | 2026-07-04 | 2026-10-04 | 17/4/26 | 18/5/26 | 19/5/26 | 19/8/26 | 15075000
36 | ESTABLISHMENT OF FISH FARMS WITH INPUT SUPPORT (FEEDS, NETS,) IN THE 21 LGA ACROSS THE 3 SENATORIAL DISTRICTS |  | WORKS | 2026-11-05 | 14/5/26 | 18/5/26 | 2026-08-06 | 2026-09-06 | 2026-12-06 | 19/6/26 | 20/7/26 | 21/7/26 | 21/10/26 | 2424000